Purpose / Scope:

Project timelines are built today by copying tasks in MS Project. This specification defines how PLM2 and the SEP project database generate the timing for project members from standard blocks instead: the standard steps are defined once, the project only enters its molds, parts, team and anchor dates, and only project-specific work is planned by hand. It records what the analysis of the G6x timeline found, the requirements with their acceptance test, what PLM2 already has, and a traceability matrix from every requirement to its implementation.

Owner / involved:

- C. Demmler, Process Development: owner of PLM2 and of this specification, keeps the trace current

- Project Manager of project 1748 (author of the G6x timeline): reviews the blocks, pilot user

- Program Management: users of the project timing, sign off the requirements

- Quality / APQP: PPAP and capability steps, SEP gate content

- Process Engineering, Metrology, Packaging, Toolshop, Production Planning: owners of the steps in the blocks

1. Starting point: the G6x timeline (analysed 10/02/2026)

File: G6x Project Timeline (2026-09-30).mpp, MS Project, 239 tasks, 29 resources, 04/06 to 11/11/2026. It covers the G45 WHL transfer, three mold engineering changes (3360, 3349, 3369) and ten G67 mold launches.

| Pattern | Rows | What it really is |
| --- | --- | --- |
| G67 mold launch: 9 molds x the same 11 steps (+1 partial) | ~104 | One standard block, applied 9 times |
| Cpk split per characteristic (weight, thickness, SPC 1-6) | 24 | A checklist on one task |
| iPQ elements 0.1 to 5.6, identical dates and owner | 15 | The PPAP / iPQ element checklist |
| ISIR documents (CP, WI, gauge WI, part history, cover sheet) | ~8 | Same checklist |
| Mold changes 3360 / 3349 / 3369 | ~55 | Engineering changes (ECR), planned in the project file |
| Really project-specific (BMW vehicle trial, Baxter payment, Hall 52 downtime...) | ~30 | The only part that needs hand planning |

1.1 Findings

| No. | Found in the file | Consequence |
| --- | --- | --- |
| TF-01 | 0 of 239 tasks linked, no constraints, no baseline | Every date typed by hand; a slip moves nothing and cannot be measured |
| TF-02 | Molds 3362, 3343, 3352: unpack (08/31 to 09/03) before delivery (09/03) | Impossible order, not visible |
| TF-03 | Mold 3376: no TH1; TH2 on the day of gauge validation | Missing standard step |
| TF-04 | Mold 3362: TH1 on the day of gauge validation | Dependency not respected |
| TF-05 | Mold 3377: press 1300-2 in some lines, 1300-3 in others | Copy error |
| TF-06 | Task 5.9.11 named "TH2" but is the 30-pc Cpk | Copy error |
| TF-07 | Same person as 3 resources (holmes / Chrisopher.holmes / christopher.holmes), Rautzenberg 3x, a resource named "Mold 3345: Verify correct AI Level..." | Workload per person not usable |
| TF-08 | Cpk and iPQ elements as single rows (39 rows) | Plan unreadable for the team |
| TF-09 | Mold changes planned as project tasks (~55 rows) | Duplicates the ECR process in PLM2 |
| TF-10 | One 239-line Gantt for everybody | Team members cannot see their own next tasks |

1.2 Pilot (built 10/02/2026)

In docs/project-timing/: G6x Timing Template.xlsx (block library, team, inputs, formula-driven plan, findings), G67 Timeline (from template).xml (MS Project, 99 tasks, 72 links, 14 resources) and generate.py (rebuilds both). Per mold only press, part numbers, delivery, gauge validation date and TH1 trial slot are entered. All 99 Excel dates were checked against the generator: 0 differences. Against the PM's hand-typed dates 38 of 53 are identical; the 15 others are TF-02, TF-03 and TF-04 and hand-picked unpack days.

2. Target concept

| Layer | Content | Where |
| --- | --- | --- |
| What (per gate) | SEP matrix GB-DP-0001: 7 gates, 232 work items, PM + Quality sign-off | SEP project database (in place) |
| How and when (per mold / part) | Standard blocks: steps, roles, durations, links, checklists | PLM2 block library (new) |
| Project | Molds and parts from the PDB, team (role -> person), anchor dates, project-specific tasks | PLM2 project (partly in place) |
| Changes | Mold engineering changes as ECR with their own plan; the project shows the milestones | PLM2 ECR (in place) |

Principle: nobody copies a task. A standard step exists once in a block; a project gets it by applying the block to its molds or parts. Improving a block improves every new project.

3. What PLM2 already has

| Component | Today | Gap for project timing |
| --- | --- | --- |
| Gantt 2.0 engine (plan_engine) | Links FS/SS/FF/SF with lag, constraints, working calendar, critical path, baseline, progress, idea blocks (bank build) | Runs on change plans only, not on project plans |
| SEP project database | Template copied per project: 7 gates, 232 items with department, responsible, status, audit trail; gate target date linked to a milestone | Items have no dates, durations or links; no per-mold breakdown |
| Project milestones | Name, due date, status per project | No link to tasks |
| Project team (project_responsibles) | One responsible per role per project, main / backup counting | Roles for Metrology, CMM lab, trial lead, plant layout, toolshop, production planning missing |
| Items (parts) | Tools, articles, gauges; tool produces article, gauge checks article; planned press (tool_machine), cavities, toolmaker | Tool delivery date not held |
| PPAP submission | Per part revision: level, customer, 18 elements with status and file | Only the AIAG element set; VDA iPQ set missing |
| ECR change plan | Stages 4-8 timing per change with the same engine | No standard plan template |
| Control plan characteristics | Not in PLM2 | Needed for the Cpk checklist |

4. Requirements

4.1 Block library

| No. | Requirement | Acceptance (how we test it) |
| --- | --- | --- |
| TR-01 | A block is master data: steps with ID, name, role, duration in workdays, dependency (FS/SS/FF, lag), mandatory/optional, checklist and SEP item reference. Blocks are created and edited in PLM2 without code changes. | The three pilot blocks LAUNCH, MOLDCHG, PPAP are entered in PLM2 and match the Excel pilot |
| TR-02 | Each block has an owner, a version and a status (draft / released). Changes are audited. A plan keeps the block version it was generated from; a new version reaches a running plan only when the PM applies it. | Release v2 of LAUNCH: existing G67 plan unchanged until applied |
| TR-03 | Steps name roles, never persons. The role list is the project-team role list, extended by the roles the blocks need (decision D-01). | No person is stored in any block |
| TR-04 | A step carries a checklist instead of extra rows. A checklist can be fixed text or come from data: control plan characteristics (TR-16), customer PPAP element set (TR-15). | G67 Cpk task shows weight, thickness, SPC 1-n of that part; 0 rows per characteristic |

4.2 Generating the plan from the PDB

| No. | Requirement | Acceptance (how we test it) |
| --- | --- | --- |
| TR-05 | A block is applied to items of a project: LAUNCH per tool, PPAP per part family, MOLDCHG per ECR. Task names come from the block and the item (press from the planned press, part numbers from the produces relation). | Select the 9 G67 tools -> 99 tasks, names as in the pilot |
| TR-06 | Per item only anchor dates are entered (e.g. delivery, gauge validation, trial slot). All other dates are calculated on the plant's working calendar with holidays. | G67 dates equal the Excel pilot (99 of 99) |
| TR-07 | Project-specific tasks are added by hand next to the generated ones and can be linked to them. | BMW vehicle trial linked after TH2 of mold 3349 moves with it |
| TR-08 | Items can be added or dropped later: a new tool gets its block without touching the others; a dropped one is cancelled with a reason, not deleted. | Add a 10th tool to G67: 11 new tasks, others unchanged |

4.3 Scheduling and tracking

| No. | Requirement | Acceptance (how we test it) |
| --- | --- | --- |
| TR-09 | Project plans use the Gantt 2.0 engine: links, constraints, critical path. A moved date moves its successors; nobody types successor dates. | Delay one delivery by 5 workdays: every successor moves 5 workdays |
| TR-10 | Logic checks warn about impossible order (unpack before delivery, trial before gauge) and missing mandatory steps; dropping a mandatory step needs a reason. | TF-02, TF-03, TF-04 are flagged when the G6x data is entered |
| TR-11 | A baseline is set when the plan is released. Progress and actual dates are recorded per task; slip against the baseline is visible per task and item. | Baseline + one late task shows its slip in workdays |
| TR-12 | After the baseline, moving a date asks for a reason; the change is audited (who, when, old, new, reason). | Audit list shows the move with reason |

4.4 Integration with SEP, ECR and PPAP

| No. | Requirement | Acceptance (how we test it) |
| --- | --- | --- |
| TR-13 | Each block step references one or more SEP work items (proposal in section 5). The SEP item shows the progress of its tasks over all items of the project; when all are done, closing the item is proposed to its responsible. | SEP item "Assessment of short-term capabilities CP and CPK" shows 9 of 9 Cpk tasks |
| TR-14 | SEP gate target dates are checked against the block milestones; a block milestone after its gate target is flagged. | Move gate B/RG6 before the last Cpk: warning |
| TR-15 | Mold engineering changes run as ECR; MOLDCHG is the standard template of the change plan. The project timing shows only the ECR milestones, read-only, linked to the change. | G6x sections 2-4 = 3 ECRs and 0 copied rows in the project plan |
| TR-16 | Control plan characteristics per article are held in the PDB (characteristic, type: weight / thickness / SPC, special characteristic flag) and feed the Cpk checklists. | Article 5A65DF8 shows its characteristics; its Cpk task lists them |
| TR-17 | The PPAP block's checklist is the PPAP submission's element list; the element set follows the customer (AIAG 18 elements or VDA iPQ). | BMW part shows the iPQ list of the G45 file |

4.5 Views and output

| No. | Requirement | Acceptance (how we test it) |
| --- | --- | --- |
| TR-18 | "My tasks" per person: tasks of the roles they hold on each project team, next 2-3 weeks, with main / backup counting as for ECR tasks. | Metrology sees only gauge tasks, by date |
| TR-19 | PM view: Gantt per project, filters by item, role, block; exception list (late, at risk, missing person for a role). | G67 filtered to mold 3355 shows its 11 steps |
| TR-20 | Exchange with MS Project: export as MS Project XML with links and resources (as the pilot). | Export opens in MS Project with links intact |
| TR-21 | KPIs: milestones on time (e.g. TH1, mold ready for PPAP, PPAP approval) with the calendar-day rule of the ECR KPI board. | KPI board shows on-time rate per milestone type |

4.6 Rights

| No. | Requirement | Acceptance (how we test it) |
| --- | --- | --- |
| TR-22 | The project PM edits the project plan; block library editing only by block owners and admins; team members report progress on their own tasks. | Team member cannot move another role's task |

5. Block steps against SEP work items (proposal, to confirm in the workshop)

| Step | Block step | SEP work item (gate, no.) |
| --- | --- | --- |
| L01 | Assign location in plant layout | Determine space requirements including layout (K/RG2 31, D/RG4 10, D/RG4 14) |
| L04 | Gauge validation | Create and release specifications (gauges) (E/RG3 25) |
| L06 | Complete work instructions | Create / revise test and work instructions (K/RG2 24, E/RG3 26) |
| L08 | Packaging trial / instruction | Determining and implementing the packaging and logistics concept (K/RG2 33) |
| L09 | 6-pc dimensional (CMM) | Create measurement orders, evaluate measurement reports (C/RG5 17) |
| L10 | 30-pc Cpk | Start capabilities (C/RG5 15); assessment of short-term capabilities CP and CPK (B/RG6 18) |
| L11 | Mold ready for PPAP | Start handover of series tools to the production plant (B/RG6 27) |
| P02 | ISIR / iPQ package | Initial sampling customer grade 3 (B/RG6 21); grade 1 (A/RG7 6) |
| P04 | Full PPAP approval | Assessment of long-term capabilities (A/RG7 7) |
| E01-E13 | Mold engineering change | Change management items (Sales, every gate) -> runs as ECR |

6. Steps and timing (proposal)

| No. | Step | Who | Due |
| --- | --- | --- | --- |
| S1 | Pilot: use the Excel / MS Project template for the open G67 launches | C. Demmler, PM 1748 | 10/16/2026 |
| S2 | Block workshop: steps, durations, roles, SEP mapping (section 5), decisions D-01 to D-05 | PM 1748, Quality, Process Eng. | 10/30/2026 |
| S3 | Review and sign-off of this specification | Program Mgmt., Quality | 11/13/2026 |
| S4 | Phase 1: block library, generation, engine on project plans, baseline (TR-01..12, TR-22) | C. Demmler | 02/26/2027 |
| S5 | Phase 2: SEP link, ECR milestones, control plan characteristics, PPAP element sets, my tasks (TR-13..18) | C. Demmler | 04/30/2027 |
| S6 | Phase 3: PM view and exceptions, MS Project export, KPIs (TR-19..21) | C. Demmler | 06/25/2027 |
| S7 | Acceptance: rebuild G67 in PLM2 and compare with the pilot; first new project planned only in PLM2 | PM 1748, C. Demmler | 07/30/2027 |

Phase 1 starts after the ECR go-live on 12/21/2026, so the ECR rollout is not delayed.

7. Open decisions

| No. | Decision | Who |
| --- | --- | --- |
| D-01 | Role list: extend the project team by Metrology, CMM lab, trial lead, plant layout, toolshop, production planning, or map them to existing roles | Program Mgmt., Quality |
| D-02 | Which block steps are mandatory (cannot be dropped without a reason) | Workshop S2 |
| D-03 | SEP item closing: proposed to the responsible (default) or automatic | Quality |
| D-04 | Owner of the block library: Program Management or Process Development | Program Mgmt. |
| D-05 | MS Project after go-live: export only, or also import | PM 1748 |

8. Traceability matrix (status 10/02/2026)

Every requirement is traced to where it comes from, what PLM2 already has and the evidence of its implementation. Every implementation commit names its TR number; the living copy is docs/project-timing/TRACE.md and this table is updated from it at each revision.

| No. | From | PLM2 basis | Status | Evidence |
| --- | --- | --- | --- | --- |
| TR-01 | TF-08, pilot | - | Pilot | Blocks sheet, generate.py |
| TR-02 | Concept | Audit pattern of SEP items | Open |  |
| TR-03 | TF-07 | project_responsibles | Partial | Team sheet; D-01 open |
| TR-04 | TF-08 | - | Pilot | Checklist column (text) |
| TR-05 | Pilot | Items, produces relation, tool_machine | Pilot | Plan sheet, 99 tasks |
| TR-06 | TF-01 | plan_engine calendar | Pilot | 99 of 99 dates verified 10/02 |
| TR-07 | Section 1 | Change plan free tasks | Open |  |
| TR-08 | Concept | - | Open |  |
| TR-09 | TF-01 | plan_engine (change plans) | Partial | MS Project XML: 72 links |
| TR-10 | TF-02..04 | plan_engine validation warnings | Partial | Pilot plans TH1 after gauge |
| TR-11 | TF-01 | plan_engine baseline, progress | Partial |  |
| TR-12 | Concept | Release deadline move with reason (F-02) | Partial |  |
| TR-13 | Concept | SEP work items | Partial | Mapping proposal, section 5 |
| TR-14 | Concept | SEP gate target date | Partial |  |
| TR-15 | TF-09 | ECR change plan | Partial | MOLDCHG block defined |
| TR-16 | TF-08 | - | Open |  |
| TR-17 | TF-08 | PPAP submission (AIAG) | Partial | iPQ list in PPAP block |
| TR-18 | TF-10 | My Tasks (ECR), main/backup | Partial |  |
| TR-19 | TF-10 | Gantt 2.0 UI (change plans) | Partial |  |
| TR-20 | Pilot | - | Pilot | G67 Timeline (from template).xml |
| TR-21 | Concept | ECR KPI board | Partial |  |
| TR-22 | Concept | Project team rights | Partial |  |

Status: Open = nothing yet; Partial = PLM2 has the basis, the timing function is missing; Pilot = proven in the Excel / MS Project pilot, not in PLM2; Done = in PLM2 and the acceptance test passed.