## README
G6x Timing Template: standard blocks instead of copy-paste
How it works
1. Blocks: the standard task sequences (mold launch, mold change, PPAP), with roles, durations and logic. Owned centrally, versioned.
2. Team: one role -> person map per project. Blocks never name people.
3. Inputs: per mold only press, part numbers, delivery date, gauge validation date and the TH1 trial slot (blue cells).
4. Plan: generated from the three sheets above. All dates are formulas: change an input or a duration and everything after it moves.
5. Project-specific tasks (customer trials, downtime, payment setup...) are planned by hand on top; they are not in the blocks.
Rules
- Workdays Mon-Fri; plant holidays go on the Holidays sheet.
- Cpk and iPQ elements are checklists on one task, not one row per characteristic / element.
- Mold engineering changes are ECRs: plan them in the plm2 change plan; the project shows only their milestones.
- 'PM plan' columns hold the dates from G6x Project Timeline (2026-09-30).mpp for comparison; 'Delta' = template finish minus PM finish (calendar days).
Colors: blue = input, black = formula, green = pulled from another sheet.
Source: G6x Project Timeline (2026-09-30).mpp, PM 1748, read 2026-10-02.

## Team
Role | Person | Department
Program Manager | Steven Stocks | Program Mgmt
Plant Layout | Stacy Sexton | Plant Engineering
Toolshop | Brandon Belk | Toolshop
Gauge / Metrology | Erica Gibson | Quality
CMM Lab | Erika Harris | Quality
Trial Lead | Christopher Holmes | Process Engineering
Process Engineer (WI) | Scott Damewood | Process Engineering
Packaging | Kenny Rice | Logistics
Quality Engineer | Apurva Mhetre | Quality
Production Planning | Alexa Earls | Production
Doc Control / ERP | Todd Haynes | Engineering
Tool Engineering | Matthias Rautzenberg | Tool Engineering
Purchasing | Candy White | Purchasing
Press / Plant Eng | Huascar Miranda | Plant Engineering

## Plan
Mold | Step ID | Task | Role | Person | Duration (wd) | Start | Finish | PM plan start | PM plan finish | Delta finish (days) | Checklist
[8 empty] | 2026-08-11 | 2026-08-12
[8 empty] | 2026-10-07 | 2026-10-07
[8 empty] | 2026-10-08 | 2026-10-20
[8 empty] | 2026-10-21 | 2026-10-21
[8 empty] | 2026-10-22 | 2026-10-23
[8 empty] | 2026-10-22 | 2026-10-27
[8 empty] | 2026-09-04 | 2026-09-07
[8 empty] | 2026-10-08 | 2026-10-08
[8 empty] | 2026-10-09 | 2026-10-21
[8 empty] | 2026-10-22 | 2026-10-22
[8 empty] | 2026-10-23 | 2026-10-26
[8 empty] | 2026-10-23 | 2026-10-28
[8 empty] | 2026-09-04 | 2026-09-07
[8 empty] | 2026-10-09 | 2026-10-09
[8 empty] | 2026-10-12 | 2026-10-22
[8 empty] | 2026-10-23 | 2026-10-23
[8 empty] | 2026-10-26 | 2026-10-27
[8 empty] | 2026-10-26 | 2026-10-29
[8 empty] | 2026-08-17 | 2026-08-18
[8 empty] | 2026-10-13 | 2026-10-13
[8 empty] | 2026-10-14 | 2026-10-26
[8 empty] | 2026-10-27 | 2026-10-27
[8 empty] | 2026-10-28 | 2026-10-29
[8 empty] | 2026-10-28 | 2026-11-02
[8 empty] | 2026-08-13 | 2026-08-14
[8 empty] | 2026-10-05 | 2026-10-13
[8 empty] | 2026-10-14 | 2026-10-14
[8 empty] | 2026-10-15 | 2026-10-16
[8 empty] | 2026-10-15 | 2026-10-20
[8 empty] | 2026-08-31 | 2026-09-01
[8 empty] | 2026-10-15 | 2026-10-15
[8 empty] | 2026-10-16 | 2026-10-28
[8 empty] | 2026-10-29 | 2026-10-29
[8 empty] | 2026-10-30 | 2026-11-05
[8 empty] | 2026-10-30 | 2026-11-04
[8 empty] | 2026-08-31 | 2026-09-01
[8 empty] | 2026-10-16 | 2026-10-16
[8 empty] | 2026-10-19 | 2026-10-29
[8 empty] | 2026-10-30 | 2026-10-30
[8 empty] | 2026-11-02 | 2026-11-03
[8 empty] | 2026-11-02 | 2026-11-05
[8 empty] | 2026-08-19 | 2026-08-20
[8 empty] | 2026-10-20 | 2026-10-20
[8 empty] | 2026-10-21 | 2026-11-02
[8 empty] | 2026-11-03 | 2026-11-03
[8 empty] | 2026-11-04 | 2026-11-05
[8 empty] | 2026-11-04 | 2026-11-09
[8 empty] | 2026-09-02 | 2026-09-03
[8 empty] | 2026-10-22 | 2026-10-22
[8 empty] | 2026-10-23 | 2026-11-04
[8 empty] | 2026-11-05 | 2026-11-05
[8 empty] | 2026-11-06 | 2026-11-09
[8 empty] | 2026-11-06 | 2026-11-11
Formulas:
Start = MAX(WORKDAY([Finish, row above],1,Holidays!$A2:A60))
Start = MAX(Inputs!F2,WORKDAY(H5,1,Holidays!$A2:A60),WORKDAY([Finish, row above],1,Holidays!$A2:A60))
Finish = IF([Duration (wd)]=0,[Start],WORKDAY([Start],[Duration (wd)]-1,Holidays!$A2:A60))

## Blocks
Block | Step ID | Step | Role | Duration (wd) | Depends on | Rule | Checklist / deliverable
LAUNCH: New / transfer mold launch (one per mold)
LAUNCH | L01 | Assign location in plant layout | Plant Layout | 15 | L03 | Finish the workday before L03 starts
LAUNCH | L02 | Mold delivery | Program Manager | 0 |  | Start = input 'delivery'
LAUNCH | L03 | Unpack / prep | Toolshop | 2 | L02 | Start the workday after L02 finish
LAUNCH | L04 | Gauge validation | Gauge / Metrology | 1 | L03 | Input 'gauge' if given, else after L03
LAUNCH | L05 | TH1 trial | Trial Lead | 1 | L03, L04 | Later of input 'th1' and after L03 and L04
LAUNCH | L06 | Complete work instructions | Process Engineer (WI) | 9 | L05 | Start the workday after L05 finish | WI, first piece & safe launch WI, gauge WI
LAUNCH | L07 | TH2 trial | Trial Lead | 1 | L06 | Start the workday after L06 finish
LAUNCH | L08 | Packaging trial / instruction | Packaging | 1 | L07 | Start the same day as L07 | PDS / packaging instruction
LAUNCH | L09 | 6-pc dimensional (CMM) | CMM Lab | 2 | L07 | Start the workday after L07 finish | all cavities
LAUNCH | L10 | 30-pc Cpk | Quality Engineer | 4 | L07 | Start the workday after L07 finish | Weight; Thickness; every SPC characteristic on the control plan (from PDB)
LAUNCH | L11 | Mold ready for PPAP | Program Manager | 0 | L08, L09, L10 | Milestone when L08, L09, L10 are done
MOLDCHG: Mold engineering change (belongs in the plm2 ECR plan)
MOLDCHG | E01 | Bank build for the change | Production Planning | 10 | E02 | Finish the workday before E02 starts | coverage until changed parts ship
MOLDCHG | E02 | Ship tool to toolmaker | Toolshop | 1 |  | Start = input 'tool_out'
MOLDCHG | E03 | Tool modification | Tool Engineering | 10 | E02 | Start the workday after E02 finish | duration per quote
MOLDCHG | E04 | Return tool to plant | Toolshop | 1 | E03 | Start the workday after E03 finish
MOLDCHG | E05 | Verify AI level engraved in mold | Toolshop | 1 | E04 | Start the workday after E04 finish
MOLDCHG | E06 | Change AI level in system | Doc Control / ERP | 2 | E03 | Start the same day as E03
MOLDCHG | E07 | TH trial (changed tool) | Trial Lead | 1 | E05, E06 | Start the workday after E05 and E06 finish
MOLDCHG | E08 | 6-pc dimensional (CMM) | CMM Lab | 2 | E07 | Start the workday after E07 finish | all cavities
MOLDCHG | E09 | 30-pc Cpk | Quality Engineer | 4 | E07 | Start the workday after E07 finish | Weight; Thickness; every SPC characteristic on the control plan (from PDB)
MOLDCHG | E10 | Material disposition (old level) | Production Planning | 1 | E07 | Start the same day as E07
MOLDCHG | E11 | Customer part approval / sampling | Program Manager | 1 | E08, E09 | Start the workday after E08 and E09 finish | optional: vehicle trial
MOLDCHG | E12 | Production start-up, new level | Production Planning | 5 | E11 | Start the workday after E11 finish
MOLDCHG | E13 | Changed parts delivered | Program Manager | 0 | E12 | Milestone when E12 are done
PPAP: PPAP / ISIR package (one per part family)
PPAP | P01 | Initial capability (10-pc Cpk) | Quality Engineer | 3 |  | Start = input 'trial' | Weight; Thickness; every SPC characteristic on the control plan (from PDB)
PPAP | P02 | ISIR / iPQ package | Quality Engineer | 15 | P01 | Start the workday after P01 finish | 0.1 Cover sheet; 0.2 Self-assessment; 1.3 Design/engineering approvals; 1.4 IMDS; 2.1 Process flowchart; 2.2 PFMEA; 2.3 Control plan; 3.1 Geometry/dimensions; 3.2 Material; 3.10 Reliability; 4.6 Tools; 5.1 Legal compliance; 5.4 MSA; 5.5 Part history; 5.6 Load carriers
PPAP | P03 | Validation testing (PV) | Quality Engineer | 60 | P02 | Start the same day as P02 | quote, select lab, ship samples, test
PPAP | P04 | Full PPAP approval | Program Manager | 0 | P02, P03 | Milestone when P02, P03 are done

## Inputs
Mold | Press | Part numbers | Delivery | Gauge validation | TH1 trial slot
3355 | 900-5 | 5A65DF8-03 | 2026-08-10 | 2026-10-02 | 2026-10-07
3363 | 1300-3 | 5A65E17-03, 5A65E18-03 | 2026-09-03 | 2026-10-05 | 2026-10-08
3370 | 1600-2 | 5B533A6-02 | 2026-09-03 | 2026-10-06 | 2026-10-09
3377 | 1300-2 | 9635313-02, 9635314-02 | 2026-08-10 | 2026-10-07 | 2026-10-13
3376 | 1300-3 | 9635311-02, 9635312-02 | 2026-08-10 | 2026-10-14
3362 | 1600-2 | 5A65E00-03, 5A65E00-04 | 2026-09-03 | 2026-10-15 | 2026-10-15
3343 | 1600-2 | 5A87904-02, 5A65C28-02 | 2026-09-03 | 2026-10-15 | 2026-10-16
3347 | 1300-3 | 5B6CA70-04 | 2026-08-10 | 2026-10-16 | 2026-10-20
3352 | 550 | 5B6CA81-02, 5B6CA82-02 | 2026-09-03 | 2026-10-19 | 2026-10-22
Note on F1: Press/trial slot from the press plan. Leave empty and the template plans TH1 as soon as unpack and gauge are done.

## Holidays
Plant holiday | Name | Enter plant holidays here; all plan dates skip them.

## Findings
Area | Found in the current .mpp | How the template prevents it
Links | 0 of 239 tasks are linked, no constraints, no baseline | Every date is typed by hand; a slip moves nothing and cannot be measured
Logic | Molds 3362, 3343, 3352: unpack (8/31-9/3) planned before delivery (9/3) | A link delivery -> unpack makes this impossible
Logic | Mold 3376: no TH1, TH2 on the same day as gauge validation | Template always plans TH1 after gauge
Logic | Mold 3362: TH1 on the same day as gauge validation | Template starts TH1 the workday after gauge
Naming | Mold 3377: press 1300-2 in some lines, 1300-3 in others | Press is one input field per mold
Naming | Task 5.9.11 (3352) called 'TH2' but is the 30-pc Cpk | Task names come from the block
Resources | Same person 3x: holmes / Chrisopher.holmes / christopher.holmes; Rautzenberg 3x | Roles in the block, one role -> person map per project
Resources | A resource named 'Mold 3345: Verify correct AI Level is engraved in the mold.' | Same
Granularity | Cpk split into 8 rows per characteristic (24 rows total) | One Cpk task, characteristics as checklist from the control plan / PDB
Granularity | 15 iPQ element rows with identical dates and owner | One ISIR/iPQ task with the element checklist
Scope | Mold 3360/3349/3369 changes (~55 rows) planned in the project file | These are ECRs: plan them in the plm2 change plan, show only milestones here