Purpose / Scope:

Entry point of the PLM2 implementation program at KTX Toccoa: change management, SEP / project planning, data management, lessons learned and information security move into one controlled, web-based system. In an audit this overview is shown first; the stream document of the topic is pulled next to the live system.

Owner / involved:

- C. Demmler, Process Development: owner of PLM2 and of every action in this plan, author, keeps it current

- Program Management and APQP: support (specification, tests, pilots on the running projects, evidence)

- Departments named per action (IT, Quality, Development, Tooling, HR, department heads): support where their part is needed

- Plant Management: monthly status review

1. Program at a glance

| Document | Stream | State today | PLM2 only from |
| --- | --- | --- | --- |
| TOC-PLM-01 | Change management (ECR) | Built. In test; role model being tightened | 12/21/2026 |
| TOC-PLM-02 | SEP / project database | Built. Evidence being uploaded; 1994 is lead project | 01/18/2027 (new projects) |
| TOC-PLM-03 | Data management, traceability | Core tight; remaining functions in development | 03/22/2027 |
| TOC-PLM-04 | Lessons learned | Built. Being bound into SEP and ECR | 01/04/2027 |
| TOC-PLM-05 | Information security (TISAX) | Built on company SSO and server; three points tightening | 12/11/2026 |

2. From today to target

Where we come from (brief). The information is correct today, but it lives in several places: SharePoint lists, Excel forms (GB-CM-0001, GB-DP-0001), network drives and a read-only legacy system. Not everyone can reach every source, and the link between a customer change, the part level, the tool and the gauge is kept by hand. The program closes exactly these points:

| Today | Target with PLM2 |
| --- | --- |
| Several tools, no single controlled record | One system of record per topic; old sources frozen read-only at go-live |
| Access depends on site and SharePoint rights | Web access for every department with the company account, rights by role |
| Traceability maintained by hand | Part-tool-gauge-equipment relations and revision history are system data, with where-used and audit trail |
| Timing in separate files, tasks by e-mail | Gate dates, change plans and deadlines in the record; every person sees their own tasks with due dates |

3. Master timing

Each stream runs through programming (close the remaining functions), testing (scripted acceptance test and live pilot on real projects) and finalisation (procedure released, training, old source frozen). Operation and the effectiveness review follow.

| Milestone | Meaning |
| --- | --- |
| 12/11/2026 | ECR acceptance test and G6X pilot complete; SEP gate enforcement live; TISAX points closed |
| 12/21/2026 | ECR go-live: every new change at TOC runs in PLM2 only; the SharePoint ECC list becomes read-only |
| 01/04/2027 | Lessons learned procedure released; SEP evidence of running projects uploaded |
| 01/18/2027 | SEP go-live: new projects start in PLM2 only; the Excel SEP matrix is retired for new projects |
| 03/22/2027 | Data management go-live: network drives read-only for active projects |
| 03/2027 | Effectiveness reviews per stream, reported to management review |

4. Using this in an audit

| If the auditor asks about | Pull | Show live in PLM2 |
| --- | --- | --- |
| Control of changes (IATF 8.5.6, 8.3.6) | TOC-PLM-01 | A change record: stages, hard gates, routing, timing plan, sign-offs, audit trail; G6X changes CR-2026-0001..0003 |
| Project planning, APQP, gates (IATF 8.3.2, VDA MLA) | TOC-PLM-02 | Project 1994: SEP matrix RG1-RG7, items, evidence, dual sign-off |
| Engineering specs, document control, traceability (IATF 7.5.3, 8.5.2) | TOC-PLM-03 | Part with revision history, where-used, tool and gauge relations |
| Organisational knowledge (IATF 7.1.6, 10.3) | TOC-PLM-04 | Lessons board: G6X lessons with actions and effectiveness proof |
| Information security, prototype data (TISAX, VDA ISA) | TOC-PLM-05 | Company sign-in, roles, classification, audit trail |
| Status of all of the above | TOC-PLM-LOP (KTX LOP F-DVS-CORP-010) | Open actions with owner, due date and status |

Rule until each go-live: the existing controlled forms stay valid and are filed on the PLM2 record, so control never has a gap. Where both exist, the PLM2 record leads.

5. How we implement: completed examples

PLM2 follows the same method that already brought two systems into daily controlled use at KTX Toccoa. Both run on the same company server, behind the same company sign-in, and are the record for their process today.

|  | TWOS (tooling work orders) | RFQ2 (quotation system) |
| --- | --- | --- |
| Process controlled | Tool work orders, press calls, repairs, preventive maintenance, tool handover, spare parts | RFQ costing: BOM, tooling cost, clamping force, cycle time, tool layout and machine choice, quote |
| Replaced | PowerApps apps on SharePoint lists | Excel / PowerPoint quoting without revision control |
| Users | 19 users in 6 roles (toolshop, scheduling, process technicians, managers) | Sales, engineering departments, APQP, project management |
| Live | On server 07/04/2026; system of record from 08/05/2026 (plant cutover) | System of record from 06/30/2026 |
| Data migrated | 1,230 work orders, 230 tools, 1,270 history rows, 76 spare parts | Running RFQs; awarded RFQs frozen (e.g. RFQ 26 on 09/21/2026) |
| Tests | About 775 automated backend tests | About 1,880 automated backend tests |
| Training | Classroom sessions plus training gate with sign-off records | Per department at introduction |
| Cutover control | Backup before cutover, written rollback, SharePoint kept as history only | Backup before every release; local-to-server data push disabled |
| Link to PLM2 | Tool data read by PDB; preventive maintenance status from WinCarat | Machine picks of RFQ 25 / 26 taken over into PLM2 tools (09/29/2026) |

6. Program control

- Monthly status review with Plant Management against this timing and the LOP; minutes filed in PLM2.

- A date moves only with a reason recorded in the LOP; the stream document is updated to the new status.

- Each stream closes with an effectiveness review (indicators in the stream document) reported to management review.

- Software quality: every release passes the automated test suite (about 2,000 backend and 2,900 frontend tests) before it reaches the production server; the database is backed up before every data operation.