## Findings
ID | Date | Tester | Simulation / step | Change no. | Acting as | Type | Severity | What I did | What happened (exact message) | What I expected | Screenshot file | Decision (C. Demmler) | Fix in version / LOP action | Status
F-01 | 10/01/2026 | C. Demmler (desk check / walk) | A11 |  |  | Bug | B |  | Costing: header "Waiting on cost input from 2 departments" while the Costing tab said "4 of 7 departments have not costed yet". Fixed 10/01: both name the departments that still owe an input |  |  |  |  | Done
F-02 | 10/01/2026 | C. Demmler (desk check / walk) | 6.3 |  |  | Bug | B |  | Release deadline could be moved without a reason. Fixed 10/01: "Move" asks why, the reason is required and audited |  |  |  |  | Done
F-03 | 10/01/2026 | C. Demmler (desk check / walk) | A21 |  |  | Bug | B |  | D1 tab showed the gate buttons to an admin acting as a department, then refused. Fixed 10/01: read-only while acting, with a hint |  |  |  |  | Done
F-04 | 10/01/2026 | C. Demmler (desk check / walk) | C1 |  |  | Missing | B |  | "Internal change" was greyed in the start form. Fixed 10/01: internal changes can be started; walked end to end before switching on |  |  |  |  | Done
F-05 | 10/01/2026 | C. Demmler (desk check / walk) | 8 |  |  | Process Flow | B |  | Process Flow page differed from the system in 18 points. Fixed 10/01: page aligned (section 8) |  |  |  |  | Done
F-06 | 10/01/2026 | C. Demmler (desk check / walk) | A24 |  |  | Bug | A |  | ECN check workflows, stage 3: "Implement tool change" went to Production and "Update master data & logistics" to Logistics, both retired: nobody got these tasks. Fixed 10/01 (live): Process Engineer (Tool Engineer accountable) and Scheduling, along the role remap |  |  |  |  | Done
S-001
S-002
S-003
S-004
S-005
S-006
S-007
S-008
S-009
S-010
S-011
S-012
S-013
S-014
S-015
S-016
S-017
S-018
S-019
S-020
S-021
S-022
S-023
S-024
S-025
S-026
S-027
S-028
S-029
S-030
S-031
S-032
S-033
S-034
S-035
S-036
S-037
S-038
S-039
S-040
S-041
S-042
S-043
S-044
S-045
S-046
S-047
S-048
S-049
S-050
S-051
S-052
S-053
S-054
S-055
S-056
S-057
S-058
S-059
S-060
S-061
S-062
S-063
S-064
S-065
S-066
S-067
S-068
S-069
S-070
S-071
S-072
S-073
S-074
S-075
S-076
S-077
S-078
S-079
S-080
S-081
S-082
S-083
S-084
S-085
S-086
S-087
S-088
S-089
S-090
S-091
S-092
S-093
S-094
S-095
S-096
S-097
S-098
S-099
S-100
S-101
S-102
S-103
S-104
S-105
S-106
S-107
S-108
S-109
S-110
S-111
S-112
S-113
S-114
S-115
S-116
S-117
S-118
S-119
S-120
S-121
S-122
S-123
S-124
S-125
S-126
S-127
S-128
S-129
S-130
S-131
S-132
S-133
S-134
S-135
S-136
S-137
S-138
S-139
S-140
S-141
S-142
S-143
S-144
S-145
S-146
S-147
S-148
S-149
S-150
S-151
S-152
S-153
S-154
S-155
S-156
S-157
S-158
S-159
S-160
S-161
S-162
S-163
S-164
S-165
S-166
S-167
S-168
S-169
S-170
S-171
S-172
S-173
S-174
S-175
S-176
S-177
S-178
S-179
S-180
S-181
S-182
S-183
S-184
S-185
S-186
S-187
S-188
S-189
S-190
S-191
S-192
S-193
S-194
S-195
S-196
S-197
S-198
S-199
S-200

## Process Flow check
No. | Rule (Process Flow page and system, since 10/01/2026) | Check in step | Seen in simulation (Yes / No / Other) | Tester | Comment (what you saw instead)
M1 | Hand-over to scoping (soft): description, at least one attachment, quote deadline (customer change) and a change lead | A1-A2
M2 | Into assessment: "Proceed" needs at least one R or A department, no open question or cancel vote, and the cost carrier. Soft: impacted items, lead, quote deadline. Hard: the impacted set confirmed by Development | A4-A6
M3 | The cost carrier is fixed at the scoping meeting and cannot change after scoping | A5, C1
M4 | Into costing (soft): every R/A assessment submitted, no "not feasible", no routing change pending | A9
M5 | "Not feasible" does not reject: it holds costing and offers "Reject change", "Back to scoping" (reason) or "Override with a reason" (four eyes) | C3
M6 | Moves back, each with a reason: reopen costing (from quote creation), reopen a rejected change, back from validation to implementation | C5, C9
M7 | "Customer declined" records the answer only; rejecting is its own step, and a rejected customer change closes only after the rejection letter is attached and marked sent | C4
M8 | Approval of a customer change (hard): customer accepted, PM sign-off and Quality sign-off by two different people; then "Record approval" | A14-A17
M9 | Publishing the plan is not a gate. It needs the validated timing and the bank build decision (running change, or planned scrap with a scrap price) | A19-A20
M10 | Into implementation (soft): timing validated, impact confirmed, a check workflow for every item category, D1 "Technical release?" = Yes | A21-A22
M11 | Into validation (soft): every impacted item has its revision. Open plan deviations do not stop this step | A25
M12 | Release (soft): validation checks passed, no open validation issue, every revision through its check workflow, release checklist complete, lessons step done, no open plan deviation | A28
M13 | Release deadline: set with "Customer accepted" (internal: "Approve internal costs"; Weissenburg / Solingen: their SOP), moved only with a reason | A14, 6.3
M14 | Quote deadline: needed at the hand-over and again into assessment (customer change); after capture only "Push back" with a reason; active until the offer is sent | A1-A3
M15 | On hold: "Resume" goes back to the stage it was held in, nowhere else | C6
M16 | Back to scoping (recall) only while no assessment has started, or after a "not feasible" | C3
M17 | Timing: confirmed by every department in the Team confirmation panel, validated by Sales, PM, Scheduling or the lead; it can be validated again during implementation (new baseline) | T3-T6
M18 | The engineering review lane and the intake are owned by Development | -
M19
M20
M21
M22
M23
M24
M25
M26
M27
M28
M29
M30

## Simulations run
Date | Simulation (A / B / C1-C10) | Change no. | Person A | Person B | Completed to step | Findings (IDs) | Duration (h)